## Sheet1
Deliverables | Tasks | Name | Subtasks | Estimated Duration | Actual Duration
Developing an Interactive Conversational Agent | Open a team GitHub account | Andrew Dunn | Github/Jira Setup and Integration | 0.5 hr | 0.5 hr
| Project Plan | Anamica Sunderaswara | Write project description | 0.5 hr | 0.5 hr
|  | Anamica Sunderaswara | Write rationale for SDLC chosen | 0.5 hr | 0.5 hr
|  | Anamica Sunderaswara | List all phases of the SDLC | 0.5 hr | 0.5 hr
|  | Qingyan Hu, Anamica Sunderaswara | Create a WBS | 1.5 hr
|  | Anamica Sunderaswara | Provide an explanation of the WBS | 0.5 hr
|  | Segundo Parra Jurando | Create a Gantt chart | 1 hr
|  | Segundo Parra Jurando | Provide an explanation of the Gantt chart | 0.5 hr
| Software Design | Rahman Ganiyu, Qingyan Hu | Program Designing
|  | Anamica Sunderaswara | Make a list of limitations of the program
| Project Report | ? | Include the sample output
| Project Presentation | Segundo Parra Jurando, Rahman Ganiyu | Give a live demo of the project | 10 mins
|  | Segundo Parra Jurando, Rahman Ganiyu | Give a brief overview of who did what | 5 mins
|  | Rahman Ganiyu | Show the PM graphs of the project repo
|  | Rahman Ganiyu | Show the project management tool used
| Project Programming | ? | Subtasks undetermined …